## Sheet1
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
View account list | Admin - Account management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Filter accounts by username | Admin - Account management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Filter accounts by role | Admin - Account management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Filter accounts by status | Admin - Account management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Create a new account | Admin - Account management | Medium | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Activate/Deactivate an account | Admin - Account management | Simple | Iteration 1 | SE160861 | Hồ Gia Mẫn | Iteration 1
Modify an account's details | Admin - Account management | Simple | Iteration 1 | SE160861 | Hồ Gia Mẫn | Iteration 1
Manager account management | Admin - Account management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Pagination account list | Admin - Account management | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3
View category list | Admin - Category management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Filter categories by name | Admin - Category management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Filter categories by status | Admin - Category management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Add a new category | Admin - Category management | Medium | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Modify a category's details | Admin - Category management | Medium | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
Activate/Inactivate a category | Admin - Category management | Simple | Iteration 1 | SE160867 | Trần Thị Vân Khánh | Iteration 1
View cancel ratio | Manager - Order Statistics | Simple | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View paytype graph | Manager - Order Statistics | Simple | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View statistic (Quantity, Income, Product Sold) | Manager - Order Statistics | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View statistic Graph | Manager - Order Statistics | Complex | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View top 5 best seller products | Manager - Order Statistics | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View top 5 best income products | Manager - Order Statistics | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View statistics by date range | Manager - Order Statistics | Complex | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View number of customer | Manager - Customer Statistics | Simple | Iteration 3 | SE160896 | Phạm Trung Nguyên | Iteration 2
View gender ratio of customer | Manager - Customer Statistics | Simple | Iteration 3 | SE160896 | Phạm Trung Nguyên | Iteration 3
View purchase ratio | Manager - Customer Statistics | Simple | Iteration 3 | SE160896 | Phạm Trung Nguyên | Iteration 3
View average age of customer | Manager - Customer Statistics | Simple | Iteration 3 | SE160896 | Phạm Trung Nguyên | Iteration 3
View loyal customer list | Manager - Customer Statistics | Medium | Iteration 3 | SE160896 | Phạm Trung Nguyên | Iteration 3
View list by quantity and date range | Manager - Customer Statistics | Medium | Iteration 3 | SE160896 | Phạm Trung Nguyên | Iteration 3
View products list | Manager - Product Management | Medium | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 3
Add a product | Manager - Product Management | Complex | Iteration 2 | SE160861 | Hồ Gia Mẫn | Iteration 2
Modify a product's details | Manager - Product Management | Complex | Iteration 2 | SE160861 | Hồ Gia Mẫn | Iteration 2
Modify a product's status | Manager - Product Management | Simple | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 2
Filter products by status | Manager - Product Management | Simple | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 2
Filter products by name | Manager - Product Management | Simple | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 2
Add/Delete product colors | Manager - Product Management | Simple | Iteration 2 | SE160861 | Hồ Gia Mẫn | Iteration 2
Add/Delete product sizes | Manager - Product Management | Simple | Iteration 2 | SE160861 | Hồ Gia Mẫn | Iteration 2
Upload product images | Manager - Product Management | Complex | Iteration 2 | SE160861 | Hồ Gia Mẫn | Iteration 2
Delete product images | Manager - Product Management | Complex | Iteration 2 | SE160861 | Hồ Gia Mẫn | Iteration 2
Pagination product list | Manager - Product Management | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 2
View orders list | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 2
Filter orders by customer's name | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 2
Filter orders by status | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 2
Filter orders by time range | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 2
Update an order's status | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 2
View an order's detail | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
View an order's status update time | Manager - Order Management | Simple | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Return a product | Manager - Order Management | Complex | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Change a product | Manager - Order Management | Complex | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
View return product history | Manager - Order Management | Medium | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Pagination order list | Manager - Order Management | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3
Sign up | Customer - User Authentication | Medium | Iteration 1 | SE160861 | Hồ Gia Mẫn | Iteration 1
Sign up OTP validation | Customer - User Authentication | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3
Log in | Customer - User Authentication | Simple | Iteration 1 | SE160861, SE160867 | Hồ Gia Mẫn, Trần Thị Vân Khánh | Iteration 1
Log in by Google | Customer - User Authentication | Complex | Iteration 2 | SE160839 | Lê Vũ Lâm Duy | Iteration 2
Forgot password | Customer - User Authentication | Complex | Iteration 2 | SE160947 | Tống Đức Trung | Iteration 2
Log out | Customer - User Authentication | Simple | Iteration 3 | SE160861 | Hồ Gia Mẫn | Iteration 1
View own profile | Customer - Profile Management | Simple | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 3
Modify profile's information | Customer - Profile Management | Simple | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 3
View product new list | Customer - Shoping | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View product trend list | Customer - Shoping | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View product best seller list | Customer - Shoping | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View product sale list | Customer - Shoping | Medium | Iteration 2 | SE160896 | Phạm Trung Nguyên | Iteration 2
View a product's details | Customer - Shoping | Medium | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
View a product's review | Customer - Shoping | Simple | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
View customer order history | Customer - Shoping | Complex | Iteration 3 | SE160861 | Hồ Gia Mẫn | Iteration 3
View customer order history detail | Customer - Shoping | Complex | Iteration 3 | SE160861 | Hồ Gia Mẫn | Iteration 3
Review a product | Customer - Shoping | Medium | Iteration 3 | SE160896, SE160947 | Tống Đức Trung, Phạm Trung Nguyên | Iteration 3
Order confirmation email | Customer - Shoping | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3
Pagination search-catalog page | Customer - Shoping | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3
Pagination discoverry page | Customer - Shoping | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3
Filter products by name | Customer - Product Filter | Medium | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
Filter products by price range | Customer - Product Filter | Medium | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
Filter products by colors | Customer - Product Filter | Medium | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
Filter products by sizes | Customer - Product Filter | Medium | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
View cart | Customer - Cart management | Simple | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Add to cart | Customer - Cart management | Simple | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Change quantity | Customer - Cart management | Simple | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Delete products from cart | Customer - Cart management | Simple | Iteration 3 | SE160831 | Lê Vũ Lâm Duy | Iteration 3
Check out | Customer - Payment | Complex | Iteration 2 | SE160867, SE160947, SE160831 | Tống Đức Trung, Trần Thị Vân Khánh, Lê Vũ Lâm Duy | Iteration 2
Create checkout form | Customer - Payment | Medium | Iteration 2 | SE160831 | Lê Vũ Lâm Duy | Iteration 2
Intergrate VNPay payment method | Customer - Payment | Complex | Iteration 3 | SE160867 | Trần Thị Vân Khánh | Iteration 3
Intergrate Momo payment method | Customer - Payment | Complex | Iteration 3 | SE160861 | Hồ Gia Mẫn | Iteration 3
Create contact page | Customer - Contact | Simple | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 2
Intergrate Tawk.io chatbot | Customer - Contact | Complex | Iteration 3 | SE160861 | Hồ Gia Mẫn | Iteration 2
Intergrate Google map API | Customer - Contact | Complex | Iteration 2 | SE160867 | Trần Thị Vân Khánh | Iteration 2
OTP mail | Guest | Complex | Iteration 3 | SE160947 | Tống Đức Trung | Iteration 3